## 1-Team Composition
Offshore IAM Productivity Metric – Q1 ¦ Team Composition
IAM Development | IAM Quality Assurance | IAM BAU | IAM Prod Support | Category | Value
7 | 3 | 2 | 2 | IAM Development | 7
|  |  |  | IAM Quality Assurance | 3
|  |  |  | IAM BAU | 2
|  |  |  | IAM Prod Support | 2

## 2-Project Delivery
Development – Project Delivery Performance
KPI | Current | Previous | Target
Avg Project Cycle Time (Days) | 54 | 60 | ≤65
Projects Delivered | 2 | 2 | NA
On-Time Delivery % | 92% | 90% | 90%
Rework Rate % | 4% | 5% | ≤5%
|  |  |  | Category | Current | Previous
|  |  |  | Cycle Time (Days) | 54 | 60
|  |  |  | Projects Delivered | 2 | 2

## 3-Planning & Ownership
Development – Planning & Ownership
Attribute | Measurement Criteria | Data Source | Good Benchmark
Estimation Accuracy | Planned vs actual (54 vs 50) – 8% variance | Jira | ≤10% variance
Task Ownership | Follow-ups needed – Low | Manager review | Low
Proactiveness | Issues raised early – 9 | Jira | ≥1/qtr
Scope Control | Scope creep caused – Minimal | Change logs | Minimal
|  |  |  | Category | Value
|  |  |  | Estimation Accuracy (% variance) | 8
|  |  |  | Proactiveness (issues raised) | 9

## 4-Defects & Issues
Production Support – Defects/Issues Fulfillment Performance
KPI | Value | Target
Total Defects/Issues Handled | 10 | NA
SLA Adherence | 96% | ≥95%
Avg Completion Time | 1.8 days | ≤3 days
|  |  | Category | Actual (%) | Target (%)
|  |  | SLA Adherence | 96 | 95

## 5-Request Fulfillment
Request Fulfillment Performance – BAU / Prod Support
KPI | Value | Target | Category | Value
Total Requests Handled | 19570 | — | Manual | 475
SLA Adherence | 99% | ≥95% | Automated | 19157
Avg Completion Time | 20 mins | ≤2 hrs
Manual Requests Handled | 475 (2.5%) | NA
– BI Publisher Report | 372
– Workday Dropped User Report | 25
– Monthly/Quarterly Audits | 33
– Quarterly Patching | 45
Automated Requests Handled | 19,157 (97.5%) | NA
– Daily Feed Files | 300
– Access Portal Email Notifications | 545
– Access Portal Requests | 10872
– OIM Scheduled Jobs | 7440

## 6-Workload Distribution
Workload Distribution
Category | Percentage (%) | Category | Value
OIM Integration | 35 | OIM Integration | 35
Okta Integrations | 20 | Okta Integrations | 20
BAU Support | 20 | BAU Support | 20
Production Support | 25 | Production Support | 25
Total | 100

## 7-Dashboard
Offshore IAM Productivity Metric – Q1 ¦ Dashboard
| Cat | Val | Cat | Val | Category | Current | Previous | Category | Value | Category | Actual (%) | Target (%)
| IAM Development | 7 | OIM Integration | 35 | Cycle Time (Days) | 54 | 60 | Est. Accuracy (% var.) | 8 | SLA Adherence | 96 | 95
| IAM Quality Assurance | 3 | Okta Integrations | 20 | Projects Delivered | 2 | 2 | Proactiveness (issues) | 9
| IAM BAU | 2 | BAU Support | 20
| IAM Prod Support | 2 | Production Support | 25